RMMM Plan

Risk Mitigation, Monitoring, and Management Plan

Project: Integrated Management Business Suite (IBMS)

| Version | 1.0 |
| --- | --- |
| Date | April 24, 2026 |
| Course | SEPM (Software Engineering and Project Management) |
| Team | Shivansh Srivastava – Product Developer Prahallad Padhan – Product Owner Ranveer Rai Khare – Scrum Master |
| Project | Integrated Management Business Suite (IBMS) |
| Status | Version 1.0 ¦ April 2026 |

1.  Introduction

This document presents the Risk Mitigation, Monitoring, and Management (RMMM) Plan for the Integrated Management Business Suite (IBMS) — an AI-first Enterprise Resource Planning platform built on FastAPI, Frappe, Supabase, and machine-learning services.  The plan identifies key risks, assigns probability and impact values, and specifies concrete mitigation strategies for each risk.

The plan follows the three-step process (Pressman, 2015):

Step 1 – Form a Risk Table listing all identified risks.

Step 2 – Sort risks in descending order of probability.

Step 3 – Produce a Risk Information Sheet (RIS) for each individual risk.

Risk Category Reference

| Short Form | Risk Category | Explanation |
| --- | --- | --- |
| PS | Product Size | Risks related to overall size, scale, and complexity of the software. |
| BU | Business Impact | Risks from business constraints: market conditions, competition, management. |
| CU | Customer Characteristics | Risks related to customer behaviour, expectations, and communication. |
| PD | Process Definition | Risks from unclear, undefined, or poorly followed development processes. |
| DE | Development Environment | Risks related to availability, reliability, and quality of dev tools. |
| TE | Technology to be Built | Risks from complexity, novelty, or uncertainty of the technology used. |
| ST | Staff Size & Experience | Risks related to skills, experience, and availability of the team. |

Probability Scale  &  Impact Severity

| Range; Interpretation. 80% – 100%; Very High. 60% – 79%; High. 40% – 59%; Medium. 20% – 39%; Low. < 20%; Very Low. | Lvl; Label; Description. 1; Catastrophic; Mission failure; financial loss > $500K. 2; Critical; Significant degradation; $100K – $500K. 3; Marginal; Minor degradation; $1K – $100K. 4; Negligible; Minor inconvenience; < $1K. |
| --- | --- |

2.  Step 1 – Risk Table (Initial Identification)

All identified risks are listed below with a unique ID, description, category, estimated probability, impact level, and a brief RMMM reference.

| Risk ID | Risk Description | Cat. | Probability | Impact | RMMM Summary |
| --- | --- | --- | --- | --- | --- |
| R1 | Rapid scope expansion due to evolving enterprise requirements | BU | 70% (High) | 3 – Marginal | Define and freeze scope clearly; get stakeholder sign-off; use change-contr… |
| R2 | AI/ML service integration complexity causes schedule delays | TE | 65% (High) | 2 – Critical | Spike AI/ML modules early; use containerised ML pipelines; allocate 20 % sc… |
| R3 | Data security breach or unauthorised access to sensitive business data | PS | 55% (Medium) | 1 – Catastrophic | Enforce JWT + TOTP 2FA; implement RBAC with least-privilege; run quarterly… |
| R4 | Third-party service outage (Supabase, Redis, Groq AI) disrupts operations | DE | 50% (Medium) | 2 – Critical | Implement in-memory fallback for all ERP ops; use Redis caching; configure… |
| R5 | Team skill gaps with advanced tech stack (FastAPI, Frappe, K8s, ML) | ST | 45% (Medium) | 2 – Critical | Conduct training sessions on key technologies; pair experienced devs with j… |
| R6 | Performance degradation under high concurrent user load | PS | 40% (Medium) | 2 – Critical | Load test with target concurrency before each release; use K8s HPA (3-repli… |
| R7 | Customer resistance to adopting the new integrated ERP platform | CU | 35% (Low) | 3 – Marginal | Involve key stakeholders in design reviews; provide onboarding tutorials; o… |
| R8 | Budget overrun due to underestimated infrastructure and AI API costs | BU | 30% (Low) | 2 – Critical | Perform detailed cloud-cost modelling before sprint starts; set budget aler… |

3.  Step 2 – Risk Table Sorted by Probability (Descending)

Risks re-ordered in descending probability so that the highest-likelihood risks receive the most immediate management attention.

| Risk ID | Risk Description | Cat. | Probability | Impact Level |
| --- | --- | --- | --- | --- |
| R1 | Rapid scope expansion due to evolving enterprise requirements | BU | 70% (High) | 3 – Marginal |
| R2 | AI/ML service integration complexity causes schedule delays | TE | 65% (High) | 2 – Critical |
| R3 | Data security breach or unauthorised access to sensitive business data | PS | 55% (Medium) | 1 – Catastrophic |
| R4 | Third-party service outage (Supabase, Redis, Groq AI) disrupts operations | DE | 50% (Medium) | 2 – Critical |
| R5 | Team skill gaps with advanced tech stack (FastAPI, Frappe, K8s, ML) | ST | 45% (Medium) | 2 – Critical |
| R6 | Performance degradation under high concurrent user load | PS | 40% (Medium) | 2 – Critical |
| R7 | Customer resistance to adopting the new integrated ERP platform | CU | 35% (Low) | 3 – Marginal |
| R8 | Budget overrun due to underestimated infrastructure and AI API costs | BU | 30% (Low) | 2 – Critical |

4.  Step 3 – Risk Information Sheets (RIS)

A Risk Information Sheet is produced for each of the eight identified risks.  Each sheet details sub-conditions, mitigation strategies, contingency plans, trigger criteria, and ownership assignments.

Risk Information Sheet (RIS) ¦ Risk ID: R1 ¦ Probability: 70 % (High) ¦ Impact: 3 – Marginal

| Date: 24 / 04 / 2026 | Category: BU – Business Impact | Assigned To: Prahallad Padhan (Product Owner) | Originator: Ranveer Rai Khare (Scrum Master) |
| --- | --- | --- | --- |

| Description | Stakeholders continuously request additional features beyond the agreed scope, resulting in schedule slippage and cost overrun. |
| --- | --- |
| Refinement & Context (Sub-conditions) | Sub-condition 1: Requirements were collected informally without formal sign-off. Sub-condition 2: Multiple stakeholder groups have conflicting priorities. Sub-condition 3: Market changes prompt leadership to request mid-sprint additions. |
| Mitigation & Monitoring Strategies | 1. Establish a formal Change Control Board (CCB) with documented approval workflows. 2. Baseline scope in a signed Software Requirements Specification (SRS). 3. Use backlog grooming to assess impact of every change before acceptance. 4. Set a sprint change-freeze policy: no new requirements after sprint planning. |
| Contingency Plan & Management | 1. Renegotiate project timeline and budget for every approved change. 2. Defer non-critical features to a future release roadmap. 3. Escalate to project sponsor if scope growth exceeds 15 % of baseline. 4. Initiate a formal re-baselining with an updated WBS. |
| Trigger | Approved change requests exceed 10 % of baseline story points in any sprint. |

Risk Information Sheet (RIS) ¦ Risk ID: R2 ¦ Probability: 65 % (High) ¦ Impact: 2 – Critical

| Date: 24 / 04 / 2026 | Category: TE – Technology to be Built | Assigned To: Shivansh Srivastava (Product Developer) | Originator: Ranveer Rai Khare (Scrum Master) |
| --- | --- | --- | --- |

| Description | Integration of AI/ML services (anomaly detection, fraud scoring, dynamic pricing, predictive inventory, lead scoring) is more complex than estimated, causing schedule delays and performance issues. |
| --- | --- |
| Refinement & Context (Sub-conditions) | Sub-condition 1: AI/ML libraries require dependency resolution across Python versions. Sub-condition 2: Model training data quality is lower than expected. Sub-condition 3: Real-time inference latency does not meet the ≤ 200 ms SLA. |
| Mitigation & Monitoring Strategies | 1. Allocate a dedicated 2-week AI/ML spike at the start of each milestone. 2. Containerise all ML services independently to isolate failures. 3. Implement rule-based fallback logic for each ML service if a model is unavailable. 4. Track model accuracy and latency metrics via the monitoring dashboard. |
| Contingency Plan & Management | 1. Substitute unavailable ML features with enhanced rule-based approximations. 2. Extend sprint timeline by up to 20 % buffer for AI integration blockers. 3. Reduce AI feature scope to core functions only for the initial release. 4. Engage an external ML consultant if internal team cannot resolve blockers. |
| Trigger | AI/ML integration tasks remain blocked for more than 3 consecutive days. |

Risk Information Sheet (RIS) ¦ Risk ID: R3 ¦ Probability: 55 % (Medium) ¦ Impact: 1 – Catastrophic

| Date: 24 / 04 / 2026 | Category: PS – Product Size | Assigned To: Shivansh Srivastava (Product Developer) | Originator: Prahallad Padhan (Product Owner) |
| --- | --- | --- | --- |

| Description | Unauthorised access to sensitive business data (financial records, employee data, customer PII) due to exploited security vulnerabilities in the IBMS platform. |
| --- | --- |
| Refinement & Context (Sub-conditions) | Sub-condition 1: JWT secret rotation not enforced; long-lived tokens become exploitable. Sub-condition 2: Supabase Row-Level Security (RLS) policies misconfigured for certain roles. Sub-condition 3: Third-party dependency with a known CVE included in the Docker image. |
| Mitigation & Monitoring Strategies | 1. Enforce JWT + TOTP 2FA for all admin and manager roles. 2. Run automated penetration tests quarterly; patch Critical/High CVEs within 7 days. 3. Verify and test Supabase RLS policies for every table before each release. 4. Conduct monthly dependency vulnerability scans (pip-audit / OWASP Dependency-Check). |
| Contingency Plan & Management | 1. Immediately revoke all active sessions and force re-authentication on breach. 2. Notify affected stakeholders and regulators within 72 hours per breach regulation. 3. Engage a certified incident-response team to contain and remediate the breach. 4. Perform a full post-incident security review and implement corrective controls. |
| Trigger | Audit logs show access patterns inconsistent with normal user behaviour, or a CVE with CVSS ≥ 8.0 is disclosed for a used dependency. |

Risk Information Sheet (RIS) ¦ Risk ID: R4 ¦ Probability: 50 % (Medium) ¦ Impact: 2 – Critical

| Date: 24 / 04 / 2026 | Category: DE – Development Environment | Assigned To: Shivansh Srivastava (Product Developer) | Originator: Ranveer Rai Khare (Scrum Master) |
| --- | --- | --- | --- |

| Description | Outage or degradation of critical third-party services — Supabase, Redis, Groq AI API — disrupts core IBMS operations. |
| --- | --- |
| Refinement & Context (Sub-conditions) | Sub-condition 1: Single-region Supabase deployment is a single point of failure. Sub-condition 2: Redis is not replicated; cache loss causes database overload. Sub-condition 3: Groq AI API rate limits are exceeded during peak usage. |
| Mitigation & Monitoring Strategies | 1. Implement in-memory fallback stores for all ERP ops when Supabase is unreachable. 2. Deploy Redis with a replica and configure automatic failover. 3. Cache Groq AI responses in Redis with appropriate TTL to reduce API call volume. 4. Monitor /api/health endpoint; alert the team on any dependency degradation. |
| Contingency Plan & Management | 1. Activate manual override procedures for critical business operations. 2. Switch to backup Supabase project or PostgreSQL if primary is down > 1 hour. 3. Disable AI-powered features temporarily; serve cached or default responses. 4. Communicate service status and ETA to users via an in-app notification banner. |
| Trigger | Health-check endpoint reports a dependency as unhealthy for > 5 minutes, or error rate exceeds 5 % over a 10-minute window. |

Risk Information Sheet (RIS) ¦ Risk ID: R5 ¦ Probability: 45 % (Medium) ¦ Impact: 2 – Critical

| Date: 24 / 04 / 2026 | Category: ST – Staff Size & Experience | Assigned To: Ranveer Rai Khare (Scrum Master) | Originator: Prahallad Padhan (Product Owner) |
| --- | --- | --- | --- |

| Description | Team members lack sufficient experience with FastAPI async patterns, the Frappe framework, Kubernetes, or ML model deployment, leading to low-quality code and rework. |
| --- | --- |
| Refinement & Context (Sub-conditions) | Sub-condition 1: New members unfamiliar with Frappe's hook system and DocType conventions. Sub-condition 2: Insufficient K8s experience leads to misconfigured deployment manifests. Sub-condition 3: Lack of async Python expertise causes blocking I/O anti-patterns in FastAPI. |
| Mitigation & Monitoring Strategies | 1. Conduct technology-specific onboarding workshops in the project's first two weeks. 2. Pair junior developers with a senior mentor for all critical modules. 3. Maintain an internal wiki with code patterns, pitfalls, and architectural decisions. 4. Allocate a 15 % ramp-up time buffer in the first sprint per new team member. |
| Contingency Plan & Management | 1. Engage specialist contractors for Frappe or K8s tasks if skill gap is confirmed. 2. Reduce technical scope to areas within proven team competencies for v1. 3. Obtain targeted training from certified providers (FastAPI, K8s, Frappe). 4. Reassign modules to better-matched team members based on skill audit. |
| Trigger | Sprint velocity drops > 30 % below plan two sprints in a row, or code-review defect rate exceeds 40 % for a specific module. |

Risk Information Sheet (RIS) ¦ Risk ID: R6 ¦ Probability: 40 % (Medium) ¦ Impact: 2 – Critical

| Date: 24 / 04 / 2026 | Category: PS – Product Size | Assigned To: Shivansh Srivastava (Product Developer) | Originator: Ranveer Rai Khare (Scrum Master) |
| --- | --- | --- | --- |

| Description | The IBMS platform degrades significantly under high concurrent user load, failing to serve real-time KPI WebSocket updates and ERP requests within SLA. |
| --- | --- |
| Refinement & Context (Sub-conditions) | Sub-condition 1: WebSocket broadcast to many concurrent clients is not optimised. Sub-condition 2: Supabase connection pool is exhausted under high concurrency (> 200 users). Sub-condition 3: ML inference endpoints are not horizontally scaled and become bottlenecks. |
| Mitigation & Monitoring Strategies | 1. Run load tests (Locust / k6) at target concurrency before each major release. 2. Use Kubernetes HPA to auto-scale pods based on CPU/memory metrics. 3. Cache KPI data in Redis with a 15-second TTL to reduce database load. 4. Profile and optimise Supabase queries; add appropriate indexes. |
| Contingency Plan & Management | 1. Throttle WebSocket clients and reduce KPI update frequency during peak load. 2. Scale Kubernetes replicas manually beyond HPA limits if needed. 3. Degrade gracefully: disable non-essential background jobs under high load. 4. Negotiate a temporary SLA relaxation while performance improvements are applied. |
| Trigger | P95 API response time exceeds 2 seconds, or WebSocket disconnections exceed 10 % of active connections in any 5-minute window. |

Risk Information Sheet (RIS) ¦ Risk ID: R7 ¦ Probability: 35 % (Low) ¦ Impact: 3 – Marginal

| Date: 24 / 04 / 2026 | Category: CU – Customer Characteristics | Assigned To: Prahallad Padhan (Product Owner) | Originator: Ranveer Rai Khare (Scrum Master) |
| --- | --- | --- | --- |

| Description | Enterprise clients resist adopting IBMS due to unfamiliarity with the new system, fear of data-migration risks, or preference for legacy tools. |
| --- | --- |
| Refinement & Context (Sub-conditions) | Sub-condition 1: End users were not involved in the requirements-gathering phase. Sub-condition 2: No structured change-management or training programme was planned. Sub-condition 3: Data migration from legacy systems is perceived as high risk by the IT department. |
| Mitigation & Monitoring Strategies | 1. Involve key end-user representatives in sprint demos and UAT sessions. 2. Develop comprehensive user guides and video tutorials before go-live. 3. Offer a phased rollout with a parallel-run period to build user confidence. 4. Assign a dedicated Customer Success point-of-contact for the first 3 months. |
| Contingency Plan & Management | 1. Extend the parallel-run period and delay full cutover until adoption metrics are met. 2. Provide on-site training sessions for power users at no extra charge. 3. Simplify the UI for less tech-savvy users based on usability testing feedback. 4. Set up a dedicated support channel (email / Slack) during the adoption phase. |
| Trigger | User adoption rate is below 60 % after 4 weeks of go-live, or NPS score is below 20 in the first post-launch survey. |

Risk Information Sheet (RIS) ¦ Risk ID: R8 ¦ Probability: 30 % (Low) ¦ Impact: 2 – Critical

| Date: 24 / 04 / 2026 | Category: BU – Business Impact | Assigned To: Prahallad Padhan (Product Owner) | Originator: Ranveer Rai Khare (Scrum Master) |
| --- | --- | --- | --- |

| Description | The project budget is exceeded due to underestimation of cloud infrastructure costs (GCP / AWS), AI API usage fees (Groq), and third-party service subscriptions. |
| --- | --- |
| Refinement & Context (Sub-conditions) | Sub-condition 1: Cloud resource costs were estimated at flat rates without usage-spike modelling. Sub-condition 2: Groq AI API charges are based on token volume, which was underestimated. Sub-condition 3: Supabase costs scale with database size and API requests beyond the free tier. |
| Mitigation & Monitoring Strategies | 1. Build a detailed cloud cost model using GCP/AWS calculators before each sprint. 2. Set billing alerts at 70 % and 90 % thresholds on all cloud accounts. 3. Review infrastructure costs in bi-weekly budget review meetings. 4. Maintain a 15 % contingency reserve in the project budget. |
| Contingency Plan & Management | 1. Right-size cloud resources (reduce instance types, shut unused regions) immediately. 2. Replace Groq AI with a self-hosted open-source model (Ollama / Llama) if costs spike. 3. Pause non-essential staging environments during cost-overrun periods. 4. Initiate a formal budget re-baseline request with the project sponsor. |
| Trigger | Monthly cloud spend exceeds the monthly budget by > 15 %, or cumulative project spend reaches 85 % of the total approved budget before 75 % of milestones are complete. |

5.  Summary & Review Notes

Each identified risk has an individual Risk Information Sheet (RIS) as documented above.  This RMMM Plan must be reviewed at the start of every sprint and updated whenever a risk's probability or impact changes.  New risks discovered during the project lifecycle must be added immediately with a new Risk ID and a corresponding RIS.

Probability values are consensus estimates agreed by the team using the Wideband Delphi technique.  Impact levels follow the four-tier severity scale (Catastrophic → Negligible) as defined in Pressman's Software Engineering textbook.